## Data
Task | Description | Duration (weeks) | Precedence
A | Market Study | 14
B | External Developer Focus Group | 10
C | Feature Selection | 4 | A,B
D | Hardware Engineering | 25 | C
E | Operating System Devlpt. | 16 | D,B
F | Advertising Campaign | 20 | D,M,N
G | Supplier Selection & Negotiation | 20 | D
H | Component Inventory Buildup | 45 | G
I | Assembly Facility Setup | 18 | D
J | Finished Good Inventory Buildup | 7 | I,H
K | Library & Programmer Toolkit Devlpt. | 12 | E
L | External Development Support Setup | 5 | K
M | Internal Game Devlpt. | 30 | K
N | External Game Devlpt. | 32 | L,O
O | Platform Promotion | 6 | K
P | Publisher Selection & Negotiation | 5 | M
Q | Website Setup | 20 | M
R | Release Promotion Material Design | 3 | D,M,N
S | Distribution Channels Devlpt. & Negotiation | 9 | R
T | Carrier Selection & Negotiation | 4 | S
U | Launch Event Organization & PR | 5 | R
V | Hardware & Software Shipment | 1 | J,T,P,N
W | Launch! | 0 | V,U,Q,F
What is the critical path and total duration for this project?
Suppose that a marketing study finds that the Advertising Campaign can be shortened to 15 weeks without significant impact reduction. What is the new CP and total project duration?
Suppose we would like to reduce the itme until launch to 28 months, what would you recommend?
Bonus: Suppose that the duration of the development tasks E, M and N are now random variables following exponential distributions with means 16, 30 and 32 respectively. What is the probability that the total project duration will be more than 135 weeks?